## Slide 1
MODULE 7
Ops weekly return
This is the week’s report.
Director sections feed the directors’ report.
“Works ongoing” will not sign.
Red and amber mean that part is still empty.
Quantum Facades · Hub training
Notes: This is the week’s report. Sections marked for the operations director feed the directors’ report. A one-line works ongoing will not sign. Red and amber mean that part is still empty. Open Forms, Weekly Operations, Ops Weekly Return, Fill.

## Slide 2
STEP 1
Prefill from the diaries
Open the current week.
Press Prefill from diaries.
Read what came in, and correct it.
Quantum Facades · Hub training
Notes: Open the current week. Press Prefill from diaries. Show what came in, and read it and correct it. The prefill is a draft of the week, not the finished report.

## Slide 3
STEP 2
A progress line has five parts
Block
Elevation or level
Activity
Measure
Status
Quantum Facades · Hub training
Notes: Open one progress line. It needs a block, an elevation or a level, an activity, a measure, and a status. A line that only says installing Tyvek will be rejected.

## Slide 4
STEP 3
The programme PDF, and the director sections
You cannot sign without the dropline PDF.
Programme, materials, delays and HSQE.
Delays are confirmed even when the answer is nil.
Save draft. Look at the red and amber chips.
Quantum Facades · Hub training
Notes: Show the programme dropline attachment. You cannot sign without that PDF. Show programme, materials, delays and HSQE. Delays must be confirmed even when the answer is nil. Save draft. The red and amber chips are the parts still empty.

## Slide 5
WHEN IT GOES WRONG
Prefill brings nothing, or Sign is refused
Nothing came in: the diaries are still drafts. Lock them, then prefill again.
Sign refused: read the red sections.
A missing block, measure, status, or programme PDF will stop it.
A vague one-line director section will stop it.
Quantum Facades · Hub training
Notes: If prefill brings nothing, the diaries for that week are still drafts. Lock them, then prefill again. If Sign is refused, read the red sections. A progress line is missing a block, a measure, or a status, or the programme PDF is not attached, or a director section is still a single vague line.

## Slide 6
WHEN IT GOES WRONG
HSQE is still shouting about an incident
The incident was signed but never closed out.
Close it on the incident form.
Then come back to the weekly return.
Quantum Facades · Hub training
Notes: If an incident is still shouting on the HSQE section, it was signed but never closed out. Close it on the incident form, then come back.