## Slide 1
MODULE 8
Quality forms
Acceptance, rejection and handover are the conversation with the main contractor.
The product packs are the install record.
Location first. Every line answered. A photo where the line asks for one. Then Sign and issue.
A photo on its own is not the QA record.
Quantum Facades · Hub training
Notes: Acceptance, rejection and handover are the conversation with the main contractor. The product packs are the install record. Location first, every line answered, a photo where the line asks for one, then Sign and issue. A photo on its own is not the QA record.

## Slide 2
MAIN CONTRACTOR
Acceptance, rejection, handover
Acceptance: new WAA, block, areas or masts. Email sends the PDF when you issue.
Rejection: the reason must be clear enough for the main contractor to act.
Handover: markup and area photos. It stays open until they counter-sign.
Save a draft only while you practise.
Quantum Facades · Hub training
Notes: Works Area Acceptance. Show New WAA, block, areas or masts, and Sign and issue. If Communicated by is Email, the PDF is emailed when you issue. Works Area Rejection needs a reason clear enough for the main contractor to act. Works Area Handover needs the markup and the area photos. Sign and issue to the main contractor sends them a link to counter-sign, and the handover stays open until that signature is back. Save a draft only.

## Slide 3
PRODUCT PACKS
Location first, then every line
Block, mast, level, subcontractor.
One Yes, one No, one N/A.
The evidence photo sits on the line that asks for it.
Pre-install still needs both A and B.
The template is edited once for the company, not on every sheet.
Quantum Facades · Hub training
Notes: On Product QA, show the location chips first: block, mast, level, subcontractor. Show one Yes, one No, one N/A, and where the evidence photo goes. Pre-install still needs both A and B. The template is edited once for the company, not on every sheet.

## Slide 4
WHICH PACK
The pack depends on the job
Gateway: Corofil, Supports, IKO Mansafe, Nyrok.
Parliament Place: EPDM, Promat and Y-Wall.
Tyvek: Parliament Place, Gateway, and Urban One.
If the tile is missing, that job does not use that pack.
Quantum Facades · Hub training
Notes: Corofil, fire barrier and insulation, and Supports, are on Gateway. Supports is horizontal, vertical, or both, with a photo per requirement. EPDM, and Promat and Y-Wall, are on Parliament Place. Tyvek is on Parliament Place, Gateway, and Urban One. IKO Mansafe is Gateway, with block, roof or level, and post location. Nyrok Insulation is Gateway. The tile is spelt Nyrok Insualtion. It is this pack. If a tile is missing, say which project uses it. Do not imply the job has skipped QA.

## Slide 5
WHEN IT GOES WRONG
You cannot tell which elevation it is
Location was skipped.
Go back.
Set block and level before anything else.
Quantum Facades · Hub training
Notes: If you cannot tell which elevation a sheet belongs to, location was skipped. Go back and set block and level before anything else.

## Slide 6
WHEN IT GOES WRONG
Handover will not stand, or they have not signed
Missing markup or photos: attach them to the form.
Still open: chase the counter-sign link.
Do not start a second handover to make it look signed.
Quantum Facades · Hub training
Notes: If handover will not stand, the markup or the photos are missing. Attach them to the form. If the main contractor has not counter-signed, the register still shows it open. Chase the link. Do not start a second handover for the same area to make it look signed.