## Slide 1
MODULE 13
Daywork stays in order
The project manager drafts.
The QS confirms it is not already in the measured works.
The project manager issues.
The subcontractor fills labour on a link. They do not log in.
The project manager signs. The QS values.
Quantum Facades · Hub training
Notes: Daywork is six steps, and they stay in order. The project manager drafts the instruction. The QS confirms the work is not already in the measured works. The project manager issues it. The subcontractor fills the labour on the link. The project manager signs that labour. The QS values it. A site login cannot do the QS steps. An operations login cannot issue the instruction. Open Daywork from the site menu.

## Slide 2
THE SIX STEPS
Read the banner, then the chips
The banner shows which role is signed in.
PM drafts, QS confirms, PM issues.
Subcontractor labour, PM signs, QS values.
Send the labour link. Do not ask for a Hub password.
Quantum Facades · Hub training
Notes: Read the banner at the top so you can see which role is signed in. The six chips are PM drafts, QS confirms, PM issues, Subcontractor labour, PM signs, QS values. The labour link is what you send. You do not ask the subcontractor for a Hub password. Open it in a private window. The register shows status, claimed, and QS valued.

## Slide 3
THE INSTRUCTION
What the draft has to say
Project, client, labour subcontractor.
Location and date.
Discussed by the QFL project manager and the QS.
Recoverable, the description, and why it is additional.
Quantum Facades · Hub training
Notes: Press New instruction only if you are happy to leave a draft. Otherwise open an existing row. The fields are project, client, labour subcontractor, location, date, discussed by the QFL project manager and the QS, recoverable, description, and why it is additional.

## Slide 4
WHEN IT GOES WRONG
The wrong login, or the work is already measured
The page is for the project manager, the QS, and admin.
QS confirm and value need an operations login.
Do not tick the QS confirmation yourself.
If the QS says it is in the measured works, it is not issued as daywork.
A subcontractor already logged into the Hub opens the link in a private window.
Quantum Facades · Hub training
Notes: If the page says it is for the project manager, the QS, and admin, and this login is none of those, stop. The right person records this. If you are the project manager, the QS steps are not yours. Switch to an operations login for confirm and value. Do not tick the QS confirmation yourself to get the instruction out. If the QS has left a note that the work is in the measured works, the instruction does not get issued as daywork. Read the note on screen. If the subcontractor cannot open the link while logged into the Hub as someone else, use a private window.